## 1 Main data
IPA CBC BULGARIA-SERBIA QUARTERLY REPORT
Project code |  | 2007CB16IPO006-2011-2-88
Project acronym |  | ELIOT
Priority axis |  | Axis1: Development of small-scale infrastructure
Measure |  | 1.1. Physical and information infrastructure
Project title |  | Ethnic legasy in our time
Lead Partner |  | Boljevac Municipality, Kralja Aleksandra 24 19370 Boljevac, Republic of Serbia
Starting date of the project |  | 30.07.2014.
End date of the project |  | 30.01.2016.
Reporting Period
from |  | 30.07.2014.30 | to
|  | 30.07.2014. |  | 30.10.2014.
Legal representative of the Lead partner
First Name | Nebojša |  | Family Name | Marjanović
Position | Mayor
Telephone | 38130463412 |  | Fax | 38130463412
E-mail | kabinet@opstinaboljevac.rs
|  | 14.11.2014. | Date & Signature
Statement of the Lead partner
By submitting the present Report, I, the undersigned, representing the Lead Partner hereby declare that:
1. The expenditure presented by this Report has been incurred only for the purpose of implementing the Project and the activities presented correspond to the activities of the approved Application;
2. The expenditure declared in the present Report has not been included in any other previous Report;
3. The information and documentation in this progress report and its attachments give a correct description of the implementation and the present status of the project part.

## 2 Activity report
2. ACTIVITY REPORT
2.1. Summary of the project activities
(List the activities as per the AF/Subsidy Contract from the start of the project till the end of the current reporting period)
No. | Planned activities as per AF |  | Responsible partner | Location of execution | Realised activities in the reporting period |  | Outputs delivered in the reporting period | Differences between realised activities and the work plan, their reasons and their justification
1 | Construction and equipment of info training etno-centries in Boljevac |  | Boljevac Municipality | Boljevac (Ilino), R. Serbia | Selection of consultant for preparation of tender documentation; preparation of tender for construction; publishing the tender |  | Contract between Municipality Boljevac and "Manifesto" association (consultant for tender documentation preparaion); documentation of tender package; letters of invitation to bidders and e-mail comunication with bidders | Completed within the stipulated time frame
2 | Upgrading and adaptation of info training etno-centre in Kula |  | Kula Municipality | Kula, R. Bulgaria | Selection of consultant for preparation of tender documentation; Preparation of tender dossier for construction; Marketing research elaborated and list of companies to be invited prepared. |  | Contract between Municipality Kula and consultant Maria Mirova - Georgieva (Layer) for tender documentation preparaion; Documentation of tender package prepared; Letters-invitation to bidders prepared. | Completed within the stipulated time frame
3 | Set up of info point and additional tourist signalization in Ilino |  | Boljevac Municipality | Boljevac (Ilino), R. Serbia
4 | Set up of info point and additional tourist signalization in Kula |  | Kula Municipality | Kula Municipality
5 | Provision of wireless internet acces in Ilino info centre area |  | Boljevac Municipality | Boljevac (Ilino), R. Serbia
6 | Provision of wireless internet acces in Kula info centre area |  | Kula Municipality | Kula, R. Bulgaria
7 | Development of join web site |  | Boljevac Municipality | Boljevac, R. Serbia Kula, R. Bulgaria
8 | Training of local autorities reprezentatives in management of tourist destination |  | Boljevac Municipality | Boljevac (Ilino), R. Serbia
9 | Training for local stakeholders - Tourist services providers |  | Kula Municipality | Kula, R. Bulgaria
10 | Training for local stakeholders - Tourist services providers |  | Boljevac Municipality | Boljevac (Ilino), R. Serbia
11 | Press conferences at the begining and at the end of Project |  | Boljevac Municipality | Boljevac, R. Serbia | Press conference held in Kula, on the occasion of the Day of Municipality of Kula in pressence of the team members of Bulgarian and Serbian parties. The first meeting of the project team took place. |  | Record from the inaugural meeting of the Municipality of Kula. Pictures from the inaugural meeting of the Municipality of Kula; Working meeting of team members held in Kula - record from the meeting and photos of the team members. | Mutual press conference of the signatories regarding joint cooperation will be held after completed procedure of contractior selection for works in Boljevac (Ilino) and Kula. The conference will be held on the occasion of the Economic Council of the Minicipality of Boljevac, in presence of delegation from Bulgaria.
12 | Media campaing |  | Boljevac Municipality | Boljevac, R. Serbia Kula, R. Bulgaria | Boljevac - Publishing the contest for project logo; selection of the project logo according to recieved proporsals - awards. Kula- Single tender procedure conducted in the period 10.10.2014 - 10.11.2014 for "Tourist Monograph (design & print A 4)" and subcontracted suitable implementer |  | Boljevac - Text of the published logo contest; E-mails of the recieced offers. Decision of the project logo selection; Administrative document regarding payout award. Contract of services between Municipality of Boljevac and logo contest winer. Kula - Contract between Municipality Kula and consultant "Innovation and Development Center" NPO, Vidin, BG ratified for the Elaboration of Tourist Monograph for region of Kula, incl. preparation of texts, translation of texts to Serbian & English languages, proof reading & editing, realization of 32 photos, design & pre-printing; & Realization of the printing of 200 copies luxury publication: format A4, full-colour print, volume 16 pages, paper 200 gr/m2, additional varnishing | The media campaign is planned to be conducted permanently during the project duration - the logo contest is ongoing and the input for the future media campaign is formulated.
2.2. Public procurement procedures
(List the public procurement procedures - from the start of the project till the end of the current reporting period)
No. | Responsible partner | Type of procedure | Description |  |  | Amount of contract, EUR | Date of contracting - date of delivery/completion | Contractor Name
1 | Boljevac Municipality | C2 | Construction of info-training center - IN PROCEDURE
2 | Boljevac Municipality | A1 | Supervision - IN PREPARATION
3 | Kula Municipality | C2 | Construction of info-training center - IN PREPARATION
4 | Kula Municipality | A 1 | Tourist Monograph (Design and Print) - COMPLETED |  |  | 3000 | 10.11.2014 - 10.05.2015 | "Innovation and Development Center" NPO, Vidin, BG
5
6
2.3. Project Implementation timeframe
Is the project progress in line with the timeframe planned in the AF/Subsidy Contract? If not, explain and estimate the deviation. Report on delays and/or deviations from the foreseen outputs and results
All activities are carried out at the scheduled time table (Application Form 3.6. Duration and action plan) and by dynamics of individual activity that was developed at the first team meeting .
2.4. Main information and publicity activities that have been carried out during the reporting period
No. | Responsible partner | Type of communication tools/materials |  |  | Description of activity |  | Target groups | Number of persons reached
1 | Kula, R. Bulgaria | Press conference on the occasion of the Day of Municipality of Kula and Inaugural Session where the start of the project astivities has been announced |  |  | The Day of Municipality Kula and Inaugural Session where anual results have been summarized, had been the oppurtunity for official anouncment of the begining with the project activities; the ceremony was attended by project team members from Boljevac, continuing to foster friendly relations and partnership with local leaders and project team from the Municipality of Kula |  | Leadership at the local, regional and national level of the Republic of Bulgaria; citizens of the Municipality of Kula | 2 media representatives
2 | Boljevac, R. Serbia | Publication of the activities and project documents on the website of the Municipality of Boljevac |  |  | Made the public aware of the project and project activities: www.boljevac.org.rs and www.obshtina-kula.com |  | Regional public, government and civil sector | 350 visitors of the www.boljevac.org.rs and www.obshtina-kula.com for the period & 3 at least (participants of the competition for the selection of the logo project)
2.5. Project modifications
Please describe the changes in the reporting period which did not require subsidy contract modification
No. | Description of the project change |  |  |  |  | Justification
1 | Team mebers replacement conducted on behalf of Partner 2 Munucipality Kula; Letter request sent № 02-153/II - 11.09.2014 to the Managing Authority(MA).Letter - approval № 99-00-2-1571/24.09.2014 from the MA received. The following replacements were effected: the expert is Ms. Valya Penkova Tsankova, qualification economist, officer at ESGRAON services of Municipality Kula, was replaced by Mr. Tsvetelin Parvanov Todorov, qualification Economist, English & Serbian language knowledge, senior expert "Management, planning and project development" at Municipality of Kula.
2
2.6. Other issues
Please describe any suggestions, comments, difficulties or problems encountered during the project implementation, solutions, partnership relations, etc.
None for the period.

## 3 Indicators
3. INDICATORS
Please, list the outputs and results achieved as per the approved AF/Subsidy Contract from the start of the project till the end of the reporting period
3.1.OUTPUTS
General indicators as per the AF for the respective measure |  |  | Planned (target) value | Actual (achieved) value | Comments
1 | Number of small-scale projects addresing physical infrastructure improvment |  | 2 |  | the implementation period is in progress
2 | Number of small-scale projects addresing information infrastructure improvment |  | 3 |  | the implementation period has not begun yet
3 | Number of existing facilites upgraded |  | 1 |  | the implementation period is in progress
4 | Number of institucions/bodies reached by programme activities |  | 2 |  | institucions/bodies reached by programme activities is Municipality of Boljevac, Republic of Serbia and Municipality of Kula, Republic of Bulgaria
5 | Training place created |  | 2 |  | the implementation period has not begun yet
6
7
8
9
10
Project specific output indicators |  |  | Planned (target) value | Actual (achieved) value | Comments
1 | number of info point set |  | 2 |  | the implementation period is in progress
2 | number of tourist sings set |  | 10 |  | the implementation period has not begun yet
3
4
5
3.2. RESULTS
General indicators as per the AF for the respective measure |  |  | Planned (target) value | Actual (achieved) value | Comments
1 | Improved small-scale infrastructure |  | 2 |  | the implementation period is in progress
2
3
4
5
6
7
8
9
10
Project specific result indicators |  |  | Planned (target) value | Actual (achieved) value | Comments
1 | Number of joint services established (web site) |  | 1 |  | the implementation period has not begun yet
2 | incresed capacities of local authorities and stakeholders in tourism area |  | 14 |  | the implementation period has not begun yet
3 | improved environment for development of realitionships and sharing best practices across the border |  | 1 |  | explanation note to MA, No.: 337-4/2014-II/14.11.2014.
4 | citizens informed about Project activities and results |  | 5 | 3 | participants of the competition for the selection of the logo project
5
3.3. CROSS-BORDER CHARACTER
How has the cross-border character (joint development, joint implementation, joint financing, joint staffing) been reflected during the reporting period?
The project team members (5 represents from Municipality of Boljevac and 2 from Municipality of Kula) held (untill now) one meeteng in Kula on the occasion of the Day of Municipality of Kula (record from the meeting). On its first meeting, the project team has developed the time table of activities and established a model of communication. The e-mail and telephone communication between two partners is countinious. Each partner realizes the procedural activities related to the development of physical and information infrastructure and communication with local stakeholders, for itself. The Municipality of Boljevac had claimed the first 10% of the funds from the Programme and transferred the funds to the partner.
3.4. PROJECT COHERANCE WITH APPLICABLE NATIONAL/REGIONAL/EU PROGRAMMES
Ministry of State Administration and Local Self Government of Republic of Serbia and the National Agency for Regional Development (NARR) has developed the Program of supporting the implementation of measures of regional and local importance in 2014. Through the Public call for grants for measure 3, item: Urban-rural projects, the Municipality of Boljevac has provided 35% of the funds (1,328,020.00 RSD) for co-financing the CBC project "Ethno legacy in our time".
3.5. PROJECT PARTNERSHIP COOPERATION
Please indicate any synergies exhibited with other projects funded by IPA or by other programmes and describe concrete cooperation activities.
Name of project/funded by (name of Programme) |  | Description of synergies and cooperation activities
3.6. HORIZONTAL THEMES
Please present how EQUAL OPPORTUNITIES are observed (if applicable during the reporting period)
Gender balance - The project team is formed by respecting the principle of provision of equal opportunity. The same case will be in a selection process of training participants from local government as well from local stakeholders.
Please report concrete steps and activities to enhance ENVIRONMENTAL PROTECTION (if applicable during the reporting period)
The construction and adaptation of the planned infrastructure is planned (Tehnical Specifications, Volume 3. PPP documentacion) by using strictly ecological materials, by means energy efficient construction materials and ligting systems, which will icrease energy efficiency and minimise electric consumption.
Please present INNOVATIVE FEATURES, leading to new approaches, methodologies and practices (if applicable during the reporting period)
The intention of the project is to demonstrate and to adopt an innovative approach by introducing new ways in tourism management and creation of economic sustainability in the region through exchange of expiriance and ceating added value through capacity development of stakeholders in both municipalities. The report on the matter's results will be more complete in the final report.
3.7. CROSS-BORDER IMPACT (for the final report)
As a result from the project, what kind of effects can be experienced and quantified? Please detail the further effects expected and compare to the ones described in your application.
3.8. SUSTAINABILITY (for the final report)
Please report concrete steps and activities which will secure that the project results will be maintained and developed further after completion of the project. How the outcomes of the project could be used by other organizations?